## NEW FORMAT
CENTENARY COLLEGE DEFERRED MAINTENANCE AND CAPITAL NEEDS
2019-2023 5-YEAR PLAN
Total All Cost:
|  |  | Priority 1 | Priority 2 | Priority 3 | Priority 4 | Priority 5 | 5 Year Total | Years 6+ | Total All
CENTENARY COLLEGE DEFERRED MAINTENANCE
FY2019-2023 5-YEAR PLAN
|  |  | fy2018-2019 | fy2019-2020 | fy2020-2021 | fy2021-2022 | fy2022-2023 | 5-year Total | Years 6+ | Total
|  | Academic and Support Buidings | 409500 | 332000 | 267000 | 315000 | 468000 | 1747500 | 6530000 | 9009500
|  | Athletic Buildings | 71800 | 37000 | 10000 | 110000 | 60000 | 288800 | 2540000 | 2828800
|  | Resident Halls | 68000 | 181000 | 275000 | 125000 | 25000 | 524000 | 7400000 | 7924000
|  |  | 549300 | 550000 | 552000 | 550000 | 553000 | 2560300 | 16470000 | 19762300
Note: The list below identifies known deferred maintenance for each building. Many of the projects are directly related to deferred maintenance while others also include building enhancements. Fire Code, ADA, system failures and energy conservation are major factors in our projects. Priorities can adjust year to year based on most critical needs and available funding.
|  |  | Priority 1 | Priority 2 | Priority 3 | Priority 4 | Priority 5 | 5-YEAR |  | TOTAL DEF.
Deferred Maintenance List: |  |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL | YEARS 6+ | MAINT | DISCRIPTION/JUSTIFICATION
ACADEMIC AND SUPPORT FACILITIES
Anderson Choral
|  | Paint Halls |  | 15000 |  |  |  | 15000 |  | 15000
|  | Install Energy Controls |  |  |  |  | 25000 | 25000 |  | 25000 | Work to complete energy controls project.
|  | Convert lighting to LED | [5 empty] | 0 | 80000 | 80000 | High lights need change out with LED
Paint Halls
Brown Chapel
|  | Roof Replacement |  |  | 40000 |  |  | 40000 |  | 40000 | Roof beginning to age, singles becoming bare.
|  | Electricial Panel Updates |  |  |  | 25000
|  | Air Handler #2 Replacement |  |  |  |  | 50000 | 50000 |  | 50000 | Smal air handler needs replaced, and controls added.
|  | Replace Windows in Sanctuary | [5 empty] | 0 | 75000 | 75000
|  | Replace Carpet | [5 empty] | 0 | 25000 | 25000 | Carpet startg to show its age.
|  | Renovate Meeting Rooms in Back of Church | [5 empty] | 0 | 10000 | 10000 | Paint, flooring and HVAC.
Bynum Commons
| Capital | Replace Equipment | 40000 | 25000 | 25000 |  | 25000 | 115000 |  | 115000 | Equipment in need of replacement. Some not working properly.
|  | Carpet/Paint-Audubon Room | 10000 |  |  |  |  | 10000 |  | 10000 | Stains and mold are our highest concern.
|  | Paint Kitchen Floor |  | 15000 |  |  |  | 15000 |  | 15000 | Floor looks in bad condition for cooking area.
|  | HVAC Study for Air Quality |  | 15000 |  |  |  | 15000 |  | 15000
|  | Compressor (replace #5 & #10) |  | 7000 |  |  |  | 7000 |  | 7000 | AC units are out of service.
|  | RTU - Condenser repair/replace |  |  | 10000 |  |  | 10000 |  | 10000 | Unit is old and noncompliant with Freon regulations.
|  | Replace lights above food stations |  |  |  |  | 3000 | 3000 |  | 3000 | Lights are missing, some out
|  | Entry Cover (Capital Request) | [5 empty] | 0 | 75000 | 75000 | Create overhang/awning to cut energy cost & dry space outside doors.
|  | Replace Student Area Dining Carpet | [5 empty] | 0 | 40000 | 40000 | Getting close to needed replacement.
Centenary Square
|  | Parking Deck Repairs-Support for Walls | 20000 |  |  |  |  | 20000 |  | 20000
|  | Re-Roof | [5 empty] | 0 | 100000 | 100000 | Roof in extremely bad shape.
|  | HVAC Controls Replacement | [5 empty] | 0 | 30000 | 30000 | HVAC controls barely function, out of date.
|  | All Restrooms Need Updating/ADA | [5 empty] | 0 | 100000 | 100000 | Out of date. Need ADA compliance.
|  | New Boiler | [5 empty] | 0 | 100000 | 100000 | Boiler old and in bad shape.
|  | HVAC piping for Heating and Cooling Needs | [5 empty] | 0 | 150000 | 150000 | HVAC piping is old and leaks.
|  | Replace Ceilings in Halls | [5 empty] | 0 | 5000 | 5000 | Old tile.
|  | New Flooring in Hall/Offices | [5 empty] | 0 | 80000 | 80000 | Update interior.
**Complete Renovation or Replacement Needed
Facilities Services
|  | Reroof Grounds Building | 15000 |  |  |  |  | 15000 |  | 15000 | Roof in bad shape and has holes in it.
|  | (2) Trucks | 56000 |  |  |  |  | 56000 |  | 56000
|  | Lift Truck for Building Maintenance | [5 empty] | 0 | 40000 | 40000 | Lift that will allow us to safely maintain building exteriors and trees.
|  | New Facilities Tractor | [5 empty] | 0 | 20000 | 20000 | Replace an old unreliable tractor.
Feazel Building
|  | Re-roof (Possibly a sloped Roof) |  | 20000 |  |  |  | 20000 |  | 20000 | Roof has had a number of leaks. Really needs a sloped roof.
|  | Convert lighting to LED | [6 empty] | 18000 |  | Replacement needed for energy savings.
[8 empty] | 0 |  | 0
Hamilton Hall
|  | Install New Thermostats - North End | 5000 |  |  |  |  | 5000 |  | 5000 | This Completes Thermostat Replacement in the Building, Temp. Control.
|  | Waterproof East Side of Bldg. |  | 10000 |  |  |  | 10000 |  | 10000 | With West side repaired, water now on east side.
|  | Address Code Issue w/Rails on Stairs |  | 10000 |  |  |  | 10000 |  | 10000 | Fire Code Issue with Stair Railing (Fire Marshal).
|  | Reroof Building | [5 empty] | 0 | 200000 | 200000 | Roof has aged, underlayment biggest issue- leaks
Hurley Hall
|  | Replace Fan Coil Units (4 per year) |  | 20000 | 20000 | 20000 | 20000 | 80000 |  | 80000 | This would replace critical Fan Coil Unit problems over time.
| Capital | Reroof with Shingles and Repair Dormers | [5 empty] | 0 | 100000 | 100000 | Roof has exceeded life expectancy, it is worn and dormers need repairs.
|  | Paint Stairs | [5 empty] | 0 | 10000 | 10000
|  | Recarpet and Paint (5) Faculty Offices | [5 empty] | 0 | 40000 | 40000 | Areas are dated and flooring old.
|  | Replace Bldg. and Auditorium Lights with LED | [5 empty] | 0 | 40000 | 40000 | Converts all lighting to LED
|  | Replace Stairs to Front Door From Woodlawn | [5 empty] | 0 | 50000 | 50000 | Stairs are in bad shape and sinking. Not to code
|  | Install Temperature/Humidity Sensors | [5 empty] | 0 | 5000 | 5000 | To allow us to read temperatures & humidity.
| Capital | Building Needs ADA Access, Ramp and Drive | [5 empty] | 0 | 200000 | 200000 | Improved access to meet code.
| Capital | Install an Elevator | [5 empty] | 0 | 200000 | 200000 | Cost will depend on necessary building modifications.
|  | Complete Renovation of 3rd Floor | [6 empty] | 500000 | 500000 | 3rd Floor in need of renovation for program use.
**3rd Floor -Complete Renovation Needed
Jackson Hall
|  | HVAC Study for Air Quality |  | 15000 |  |  |  | 15000 |  | 15000
|  | New boiler |  |  |  |  | 75000 | 75000 |  | 75000 | Boiler is aging/ scheduled replacement.
| Capital | AC System Update/Replacement | [5 empty] | 0 | 250000 | 250000 | Humidity is becoming a problem - causing mold.
|  | New Carpet and Paint for Halls & Faculty Offices | [5 empty] | 0 | 100000 | 100000 | Carpet aging, scheduled replacement.
Marjorie Lyons Playhouse
|  | ADA restroom updates (2) in lobby |  |  | 30000 |  |  | 30000 |  | 30000 | Complaints from event attendees - no ADA access.
|  | Electricial Panel Updates, demo old |  |  |  |  | 25000 | 25000 |  | 25000
|  | Replace Air Handler | [5 empty] | 0 | 75000 | 75000 | Old, rusted and not able to set up controls.
|  | Fire/Smoke Ventilation for Stage | [5 empty] | 0 | 200000 | 200000 | Fire Marshal citations (5) for these items. Need engineer design.
| Capital | **Build-in 2nd Floor for Costumes | [7 empty] | 750000 | Storage needed, currently using rent house.
Magale Library
|  | VFD for Protection and Energy Savings | 40000 |  |  |  |  | 40000 |  | 40000 | Install energy controls-pneumatic systems failing, uncontrollable.
|  | 1st Floor Bathrooms ADA Updates | 9000
|  | Replace Tile on Front Porch | 10000
|  | Waterproofing North & South Walls |  |  |  |  | 75000 | 75000 |  | 75000 | Water intrusion from rains is damaging carpets.
|  | Ujpdate Lighting, Wiring and Fire Sprinsker Sys. |  |  |  |  | 40000 | 40000 |  | 40000 | Lighting is poor and sprinklers are needed for safety.
|  | 2nd Floor Restrooms Need Updating/ADA |  |  |  |  | 15000 | 15000 |  | 15000 | Fixtures & equipment outdated.
|  | Replace all lighting with LED | [5 empty] | 0 | 80000 | 80000
|  | New Chiller in Library Mechanical Room | [5 empty] | 0 | 150000 | 150000 | This allows for a redundant system.
|  | Replace Windows | [5 empty] | 0 | 200000 | 200000 | Building needs energy efficient windows.
Meadows Museum
|  | Replace Air Handler |  |  |  | 50000 |  | 50000 |  | 50000 | Air Handler old.
|  | Reroof Building | [5 empty] | 0 | 30000 | 30000 | Roof is aging
Mickle Hall
|  | Mech Room Wiring and Replace old Elect Panels |  |  |  |  | 50000 | 50000 | 50000 | 100000
|  | Install FCU in Halls (8 total, 2 per floor) | [5 empty] | 0 | 75000 | 75000 | Halls are hot due to lack of AC, units would greatly improve comfort.
|  | Halls - Paint Walls and Replace Carpet 2nd & 3rd fl. | [5 empty] | 0 | 75000 | 75000 | Upgrade wall treatment, replace carpet.
|  | Replace 2 AHU for Basement | [5 empty] | 0 | 150000 | 150000 | Humidity is becoming a problem, units are original to bldg. 1960
**Complete Renovation Needed
Physical Plant (Chiller Plant)
|  | Re-Roof |  |  |  |  | 25000 | 25000 |  | 25000
|  | Add Chiller for Redundancy and Dorms | [5 empty] | 0 | 150000 | 150000 | One Chiller leaves possible outage, adds support for dorms.
[8 empty] | 0 |  | 0
Sam Peters
|  | Re-roof |  |  |  |  | 20000 | 20000 |  | 20000 | Roof has aged.
Smith Hall
|  | Replace (2) old AHUs in attic | [5 empty] | 0 | 150000 | 150000 | Units are old and 2 pipe systems, need 4 pipe systems.
|  | Replace Hall Carpet | [5 empty] | 0 | 40000 | 40000 | Upgrade lighting for energy efficiency & replace carpet.
|  | Texture and Paint Walls in Halls | [5 empty] | 0 | 40000 | 40000 | Update halls with repainting.
Student Union
|  | Install Energy Controls | [5 empty] | 0 | 25000 | 25000 | Add new energy controls to SUB.
|  | New Boiler | [5 empty] | 0 | 70000 | 70000 | Priority for boiler replacement. Exceeded life expectancy
|  | New Chiller - 90 Ton | [5 empty] | 0 | 75000 | 75000 | Scheduled replacement, aging
|  | Postal Box Replacements | [5 empty] | 0 | 22000 | 22000 | Quoted price from "Salbury".
Turner Arts
|  | Install Emergency/ADA Exit Door in shop |  |  | 7000 |  |  | 7000 |  | 7000 | Needs Emergency exit and ADA access.
|  | Air Filteration System (Pottery Barn) |  |  |  |  | 5000 | 5000 |  | 5000 | For improved air quality
|  | Air Filteration System (Basement shop) |  |  |  |  | 5000 | 5000 |  | 5000 | For improved air quality
|  | Cutting Equip. Dust Collection (Basement Shop) | [5 empty] | 0 | 25000 | 25000 | Replace non-compliant Equipment
|  | Replace Flooring in Hallways and 2 classrooms | [5 empty] | 0 | 30000 | 30000 | Flooring in bad shape, floors shift, needs carpeting.
|  | Replace Classroom Carpet/Paint | [5 empty] | 0 | 50000 | 50000 | Flooring in bad shape, floors shift, needs carpeting.
|  | Concrete Floor in Basement Shop | [5 empty] | 0 | 25000 | 25000 | Work area is dirt and needs Concrete flooring, not sealed to crawl space.
**Complete Renovation Needed
[8 empty] | 0 |  | 0
Wright Building
|  | Structural repairs/leaks | [5 empty] | 0 | 50000 | 50000 | Building is shifting, doors won't open, walls cracked.
|  | Gutters and roof | [5 empty] | 0 | 25000 | 25000 | Repair gutters/roof.
|  | Replace flooring and Window blinds | [5 empty] | 0 | 75000 | 75000 | Building needs new flooring, HVAC, painting & roofing.
|  | Repair and Paint walls | [5 empty] | 0 | 40000 | 40000 | Walls are in Need of Repairs. New paint.
|  | Retaining wall replacement | [5 empty] | 0 | 10000 | 10000 | Retaining wall is falling in.
**Complete Renovation or Replacement Needed
2910
**Complete Renovation or Replacement Needed
Campus Wide
|  | Electrical survey | 50000 |  |  |  |  | 50000 |  | 50000
|  | Replace Underground Electricial & Transformers | 100000 | 110000 | 110000 | 110000 |  | 430000 |  | 430000 | Much of the irrigation is old, lines cut needs repairs.
|  | Replace Classroom Chairs | 15000 | 15000 | 15000 | 15000 |  | 60000 |  | 60000 | Replace/renovate air handlers
|  | Install LED lighting | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | 25000 | 75000 | Add ADA ramps to buildings for access (Magale & James)
|  | Reroof Gazebo | 9500 |  |  |  |  | 9500 |  | 9500
|  | Elevator Repairs-Phones, pit ladders & Pumps, etc | 20000 |  |  |  |  | 20000 |  | 20000
|  | Mechanical Room Circulating Pumps/VFD |  | 30000 |  |  |  | 30000 |  | 30000 | Bollards are old, some not working. | 90000
|  | Bollard Lights Need Replaced |  | 5000 |  | 10000 |  | 15000 |  | 15000 | Replaces old furniture
|  | Mechanical Room leaking valves |  | 25000 |  |  |  | 25000 |  | 25000 | Convert to LED for energy savings.
|  | Electricial Termographic Hot Testing (every 3yrs) | 0 |  |  | 25000 |  | 25000 |  | 25000
|  | Correct drainage around buildings |  |  |  | 50000 |  | 50000 | 50000 | 100000
|  | Replace Vault Transformers at Hardin (Switch), James, MLP, Library, Mickle and Cline | [5 empty] | 0 | 1000000 | 1000000
|  | Air Handlers | [5 empty] | 0 | 500000 | 500000 | Add signage in buildings to meet ADA code.
|  | Update Signage in Buildings | [5 empty] | 0 | 60000 | 60000 | Exterior handrails to meet ADA/Life Safety codes.
|  | Sidewalk widening & repairs | [5 empty] | 0 | 100000 | 100000 | Level landings at building entries to meet Fire Marshal codes.
|  | Handrails | [5 empty] | 0 | 100000 | 100000 | Relocate 2 power poles near Hardin to avoid damage to Oak trees.
|  | Cent. Blvd. - relocate power poles | [5 empty] | 0 | 25000 | 25000 | Campus wide electrical inspection for hot electrical panels.
|  | Update Energy Program Software & Storage | [5 empty] | 0 | 40000 | 40000
|  | Total All Projects | 409500 | 332000 | 267000 | 315000 | 468000 | 1747500 | 6530000 | 9009500
ATHLETICS:
Fitness Center
|  | Paint Pool Deck | 9200 |  |  |  |  | 9200 |  | 9200 | Deck is worn down and slick.
|  | Paint Pool Bottom | 8600 |  |  |  |  | 8600 |  | 8600 | Has not been painted since installed, faded.
|  | Paint Hall and Conference Room Ceiling | 4100 |  |  |  |  | 4100 |  | 4100
|  | Replace Compressor | 20000 |  |  |  |  | 20000 |  | 20000 | One Compressor failed, Chiller not able to cool.
|  | Chiller Repairs and New Fans | 7900 |  |  |  |  | 7900 |  | 7900
|  | Access Ramp Support Post |  | 20000 |  |  |  | 20000 |  | 20000 | Supporting structure is beginning to rust and flake
|  | Gym Floor Cover Replacement |  |  |  | 30000 |  | 30000 |  | 30000 | Carpeting is worn, stained and has frayed edges.
|  | Re-Roof Pool |  |  |  | 70000 |  | 70000 |  | 70000 | Roofing material is breaking down and aged
|  | Replace Running Track Surface |  |  |  |  | 60000 | 60000 |  | 60000 | Covering has aged, stained and looks old.
|  | Add Boiler for Pool | [5 empty] | 0 | 70000 | 70000 | Evaluate the need boiler to heat pool.
|  | Replace Tile Flooring and Carpet | [5 empty] | 0 | 75000 | 75000 | Meet its life expectancy and showing age.
Gold Dome
|  | Paint Gym, halls and Stairs | [5 empty] | 0 | 60000 | 60000 | Wall are dated. Needs fresh coat of paint.
|  | Re-tile halls and Re-carpet Offices | [5 empty] | 0 | 100000 | 100000 | Flooring is dated and damaged in some areas.
|  | Update and Renovate Locker-Rooms | [5 empty] | 0 | 100000 | 100000 | All team locker-rooms need updating
|  | Overhaul or Replace Chiller #1 | [5 empty] | 0 | 120000 | 120000 | Chiller age is becoming a concern. This replace 1 of 2.
|  | Dome needs new LED lighting. | [5 empty] | 0 | 80000 | 80000 | Need LED lighting to cut energy cost.
|  | Recoat Dome Roof | [5 empty] | 0 | 80000 | 80000 | Roof needs to be evaluated
|  | Replace old fixtures in 2 Restrooms | [5 empty] | 0 | 10000 | 10000 | Fixtures are old.
|  | Ceiling Repairs/Replacement | [5 empty] | 0 | 50000 | 50000 | Dome ceiling is in bad shape, need work.
|  | Replace Upper Level of Chairs | [5 empty] | 0 | 40000 | 40000 | Chairs are old and dated.
|  | Overhaul or Replace Boiler | [5 empty] | 0 | 75000 | 75000 | Boiler is aging, has issues to maintain temp.
|  | Parking lot Repairs/Overlay | [5 empty] | 0 | 500000 | 500000 | Parking in bad shape and limited.
|  | Overhaul or Replace Chiller #2 | [5 empty] | 0 | 120000 | 120000 | Replace chiller #2.
| Capital | Expand Parking | [5 empty] | 0 | 1000000 | 1000000 | Add parking to address shortage
| Capital | Landscape development for Dome | [5 empty] | 0 | 40000 | 40000 | Dome needs landscaping, irrigation and lighting.
[8 empty] | 0 |  | 0
McCarthy Baseball
[8 empty] | 0 |  | 0
|  | Replace or add HVAC | 4000 |  |  |  |  | 4000 |  | 4000 | HVAC unit has failed.
|  | Replace Storage Bldg. | 18000 |  |  |  |  | 18000 |  | 18000 | Building not secure and is rotting.
|  | Install new Code Compliant Exterior Stairs |  |  | 10000 |  |  | 10000 |  | 10000 | Egress is a code issue for the building.
**Complete Renovation or Replacement Needed
[8 empty] | 0 |  | 0
Baseball Complex | [7 empty] | 0 |  | 0
|  | Repairs to pressbox |  | 5000 |  |  |  | 5000 |  | 5000 | Exterior is rotting.
|  | Concession/Bathrooms Repairs |  |  |  | 10000 |  | 10000 |  | 10000
[8 empty] | 0 |  | 0 | LockerRooms, Seating, etc.
[8 empty] | 0 |  | 0
Jones Rice Practice | [7 empty] | 0 |  | 0
|  | Water Well Needed |  | 12000 |  |  |  | 12000 |  | 12000 | Water bill is high. Well to cut cost and sewage expense.
[8 empty] | 0 |  | 0
Soccer/Lacrosse | [7 empty] | 0 |  | 0
|  | Under Renovation | [5 empty] | 0 |  | 0
[8 empty] | 0 |  | 0
Softball Complex | [7 empty] | 0 |  | 0
|  | Improvements Planned | [8 empty] | Fence in bad shape.
[8 empty] | 0 |  | 0
Tennis Complex | [7 empty] | 0 |  | 0
|  | Need Practice Wall N/E Corner | [5 empty] | 0 | 20000 | 20000 | Need for practice wall and elimindate winds from damaging screens.
|  | Total | 71800 | 37000 | 10000 | 110000 | 60000 | 288800 | 2540000 | 2828800
RESIDENT HALLS:
CLINE HALL
|  | Fire Sprinkler System in Attic |  |  | 75000 |  |  | 75000 |  | 75000
|  | Mech Room Electic Panel Repalcements |  |  | 25000 |  |  | 25000 |  | 25000
|  | Replace Steps and Sidewalks |  |  | 25000 |  |  | 25000 |  | 25000 | Cracked, uneven and slanted stairs are unsafe
|  | Replace Fan Coil Units | [5 empty] | 0 | 100000 | 100000
|  | Replace plumbing to Suites | [5 empty] | 0 | 200000 | 200000
|  | HVAC Replacement Necessary | [5 empty] | 0 | 1000000 | 1000000 | Current HVAC unable to cool building in summer, no student control.
|  | Replace Parking Lot W/Concrete | [5 empty] | 0 | 175000 | 175000 | Asphalt in bad shape, has lots of repairs. Visible.
|  | Hall Director HVAC Unit | [5 empty] | 0 | 10000 | 10000 | Apartment HVAC for when building is vacant.
|  | Replace 2nd & 3rd Fl. Room doors | [5 empty] | 0 | 15000 | 15000 | Most door are in bad shape, completes to match 1st.
|  | Shower Partitions Need Repairs | [5 empty] | 0 | 15000 | 15000
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
|  | Renovate Basement for Staff | [5 empty] | 0 | 60000 | 60000 | Allow for more available beds.
HARDIN HALL
|  | Replace Carpet on Porch |  | 8000 |  |  |  | 8000 |  | 8000 | Carpet is old and stained.
|  | Mech Room Electric Panel Replacement |  |  | 25000 |  |  | 25000 |  | 25000
|  | Shower Partitions Need Repairs |  |  |  |  | 25000 | 25000 |  | 25000 | Some shower inserts need replaced. Mold/busted pans are biggest issue
| Capital | HVAC Replacement Necessary | [5 empty] | 0 | 1000000 | 1000000 | Current HVAC unable to cool building in summer, no student control.
|  | Clean, Repair & Seal Exterior Brick | [5 empty] | 0 | 75000 | 75000 | Exterior building brick stained, mortar missing and needs sealed.
|  | Hall Carpet Replacement | [5 empty] | 0 | 25000 | 25000 | Hall carpet is old and in need of replacement.
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
|  | Replace Student Room Doors | [5 empty] | 0 | 10000 | 10000 | Doors are gettig in bad shape.
JAMES ANNEX | [7 empty] | 0 |  | 0
|  | Replace Stair Treads | 7500 |  |  |  |  | 7500 |  | 7500 | Some stair treads are missing, others old.
|  | Mech Room Electric Panel Replacements |  |  | 25000
|  | Shower Partitions Need Repairs |  |  | 25000 |  |  | 25000 |  | 25000
|  | Hall Carpet Replacement | [5 empty] | 0 | 25000 | 25000 | Hall carpet is old and in need of replacement.
| Capital | HVAC Replacement Necessary | [5 empty] | 0 | 1000000 | 1000000 | Current HVAC unable to cool building in summer, no student control.
|  | Clean, Repair & Seal Exterior Brick | [5 empty] | 0 | 75000 | 75000 | Exterior building brick stained, mortar missing and needs sealed.
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
|  | Replace Student Room Doors | [5 empty] | 0 | 10000 | 10000 | Doors are gettig in bad shape.
JAMES PROPER
|  | Paint Halls and Stain Doors | 15000 |  |  |  |  | 15000 |  | 15000
|  | Mech Room Electricial Panel Replacements |  |  |  | 25000 |  | 25000 |  | 25000
|  | Shower Partitions Need Repairs |  | 25000 |  |  |  | 25000 |  | 25000
|  | Hall Carpet Replacement |  | 25000 |  |  |  | 25000 |  | 25000 | Hall carpet is old and in need of replacement.
| Capital | HVAC Replacement Necessary | [5 empty] | 0 | 1000000 | 1000000 | Current HVAC unable to cool building in summer, no student control.
|  | Clean, Repair & Seal Exterior Brick | [5 empty] | 0 | 95000 | 95000 | Exterior building brick stained, mortar missing and needs sealed.
|  | Hall Director HVAC Unit | [5 empty] | 0 | 10000 | 10000 | Apartment HVAC for when building is vacant.
|  | Lobby Asbestos Abatement/Ceiling | [5 empty] | 0 | 50000 | 50000 | The replaces old ceiling after abatement.
|  | ADA ramp into building | [5 empty] | 0 | 35000 | 35000 | Construct wheelchair accessible ramp at the NW entrance.
|  | Replace Chiller #2 | [5 empty] | 0 | 125000 | 125000 | This replace 2nd Chiller, not yet critical.
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
|  | Replace Student Room Doors | [5 empty] | 0 | 10000 | 10000 | Doors are gettig in bad shape.
ROTARY HALL | [7 empty] | 0 |  | 0
|  | HVAC System Needs Study and Full Service |  | 15000 |  |  |  | 15000 |  | 15000 | HVAC needs full service and repairs.
|  | Replace Rotten wood on Dormers/Eaves |  | 50000 |  |  |  | 50000 |  | 50000 | A number of areas aroud the building have rotten wood/.
|  | Replace Chiller |  |  |  | 100000 |  | 100000 |  | 100000 | Chiller is one of the oldest on campus.
|  | Shower Updates | [5 empty] | 0 | 30000 | 30000 | Bathroom ad shower stalls needs repairs and updates.
|  | Hall Carpet Replacement | [5 empty] | 0 | 40000 | 40000 | Hall carpet is old ad need of replacement.
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
SEXTON HALL | [7 empty] | 0 |  | 0
| Capital | Install ADA Automatic Front Door | 7500 |  |  |  |  | 7500 |  | 7500 | Necessary for ADA access by wheelchair.
| Capital | Replace Lobby Carpet | 8000 |  |  |  |  | 8000 |  | 8000 | Carpet old and bleached.
|  | ADA access - add suite, updates | 30000 |  |  |  |  | 30000 |  | 30000 | Handicap student can't access area, needed updates.
|  | Mech Room Electric Panel Replacements |  | 25000 |  |  |  | 25000 |  | 25000
|  | Shower Partitions Need Repairs |  | 25000 |  |  |  | 25000 |  | 25000
|  | Hall Carpet Replacement/Porch |  | 8000 |  |  |  | 8000 |  | 8000 | Hall carpet is old ad need of replacement.
|  | Clean, Repair & Seal Exterior Brick |  |  | 75000 |  |  | 75000 |  | 75000 | Exterior building brick stained, mortar missing and needs sealed.
| Capital | HVAC Replacement Necessary | [5 empty] | 0 | 1000000 | 1000000 | Current HVAC unable to cool building in summer, no student control.
| Capital | Asbestos Abatement/Painting | [5 empty] | 0 | 300000 | 300000 | Final resident hall to have asbestos removed.
|  | Window Replacement for Energy | [5 empty] | 0 | 200000 | 200000 | Windows broken and not energy efficient.
|  | Replace Student Room Doors | [5 empty] | 0 | 10000 | 10000 | Doors are gettig in bad shape.
|  | Resident Hall Total: | 68000 | 181000 | 275000 | 125000 | 25000 | 524000 | 7400000 | 7924000

## Capital Projects
Hamilton | Replace Flooring, Paint, Restroom Updates | 140000 | 140000 | 140000 | Building Badly Needs Updates.
| Restrooms (4) ADA updates | 60000 | 60000 | 60000 | Building is noncompliant, renovation needed.
Hurley | Recarpet/Paint Classrooms | 75000 | 75000 | 75000 | Areas in need of renovations.